## Projekt
PSE Team A
[7 empty] | Hervorgehobener Zeitraum: | [7 empty] | 1 |  |  |  | Geplant |  |  |  | Ist
|  | GEPLANTE(R) | GEPLANTE | IST- | IST- | PROZENT
| AKTIVITÄT | BEGINN | DAUER | BEGINN | DAUER | ERLEDIGT | ZEITRÄUME
| INKLUSIVE TESTS |  | IN TAGEN |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Ben | MainWindow, FilterTab | 1 | 3 |  |  | 0%
Johannes | FrameView | 1 | 2 |  |  | 0%
Noel | FilterList, FilterConfigurationLoader, FilterConfigurationSaver | 1 | 2 |  |  | 0%
Sascha | YUVFileReader, YUV411FileReader, Compression, YUV411Vector | 1 | 2 |  |  | 0%
Carina | GraphWidget, Graph | 1 | 3 |  |  | 0%
Simon | VideoLoader, AVVideo | 1 | 3 |  |  | 0%
Johannes | Video, VideoPlayer | 3 | 2 |  |  | 0%
Noel | FilterApplier, 5 Ffmpeg Filter | 3 | 3 |  |  | 0%
Sascha | YUV420FileReader, Project, YUV422Vector, YUV444Vector | 3 | 2 |  |  | 0%
Ben | AnalysisTab, AnalysisBoxContainer, AnalysisBox | 4 | 4 |  |  | 0%
Carina | PSNRCalculator | 4 | 3 |  |  | 0%
Simon | VideoConverter | 4 | 2 |  |  | 0%
Johannes | Timer, ControlPanel, PlayerControlPanel, PreviewControlPanel | 5 | 3 |  |  | 0%
Sascha | YUV422Reader, YUV444Reader | 5 | 3 |  |  | 0%
Noel | 5 Ffmpeg Filter | 6 | 2 |  |  | 0%
Simon | MacroblockCalculator | 6 | 4 |  |  | 0%
Carina | BitrateCalculator | 7 | 3 |  |  | 0%
Sascha | YUV420FileSaver, YUV411FileSaver | 8 | 3 |  |  | 0%
Noel | 5 Ffmpeg Filter | 8 | 2 |  |  | 0%
Ben | FilterConfigurationBox, 5 Filter Boxen | 8 | 2 |  |  | 0%
Johannes | YUVFileSaver, YUVFileOpenDialog, YUVInfoDialog | 8 | 3 |  |  | 0%
Simon | RGBHistogram | 10 | 2 |  |  | 0%
Carina | RGBDifferenceCalculator | 10 | 3 |  |  | 0%
Noel | 7 Ffmpeg Filter | 10 | 3 |  |  | 0%
Ben | 8 Filter Boxen | 10 | 2 |  |  | 0%
Sascha | AnalysisBoxMemento, AnalysisBoxContainerMemento | 11 | 2 |  |  | 0%
Johannes | YUV422FileSaver, YUV444FileSaver | 11 | 3 |  |  | 0%
Simon | 5 Filter Boxen | 12 | 2 |  |  | 0%
Ben | 4 Filter Boxen | 12 | 1 |  |  | 0%
Sascha | MainWindowMemento, FilterTabMemento, AnalysisTabMemento | 13 | 2 |  |  | 0%
Carina | Wunschkriterien Graphen | 13 | 3 |  |  | 0%
Alle | Undo / Redo Commands | 13 | 3 |  |  | 0%
Sascha | ProjectLoader, ProjectSaver | 15 | 3 |  |  | 0%