## Tabelle1
Aktvität | Beginn | Dauer
MainWindow, FilterTab | 1 | 3
FrameView | 1 | 2
FilterList, FilterConfigurationLoader, FilterConfigurationSaver | 1 | 2
YUVFileReader, YUV411FileReader, Compression, YUV411Vector | 1 | 2
GraphWidget, Graph | 1 | 3
VideoLoader, AVVideo | 1 | 3
Video, VideoPlayer | 3 | 2
FilterApplier, 5 Ffmpeg Filter | 3 | 3
YUV420FileReader, Project, YUV422Vector, YUV444Vector | 3 | 2
AnalysisTab, AnalysisBoxContainer, AnalysisBox | 4 | 4
PSNRCalculator | 4 | 3
VideoConverter | 4 | 2
Timer, ControlPanel, PlayerControlPanel, PreviewControlPanel | 5 | 3
YUV422Reader, YUV444Reader | 5 | 3
5 Ffmpeg Filter | 6 | 2
MacroblockCalculator | 6 | 4
BitrateCalculator | 7 | 3
YUV420FileSaver, YUV411FileSaver | 8 | 3
5 Ffmpeg Filter | 8 | 2
FilterConfigurationBox, 5 Filter Boxen | 8 | 2
YUVFileSaver, YUVFileOpenDialog, YUVInfoDialog | 8 | 3
RGBHistogram | 10 | 2
RGBDifferenceCalculator | 10 | 3
7 Ffmpeg Filter | 10 | 3
8 Filter Boxen | 10 | 2
AnalysisBoxMemento, AnalysisBoxContainerMemento | 11 | 2
YUV422FileSaver, YUV444FileSaver | 11 | 3
5 Filter Boxen | 12 | 2
4 Filter Boxen | 12 | 1
MainWindowMemento, FilterTabMemento, AnalysisTabMemento | 13 | 2
Wunschkriterien Graphen | 13 | 3
Undo / Redo Commands | 13 | 3
ProjectLoader, ProjectSaver | 15 | 3